## Delivery Plan
Better Mynd
# | Module | Sub Tasks | Pradeep Remarks | BA Hours | Development Hours | Designer Hours |  | QA Hours | Delivery | Milestone Delivery Date | Milestone Delivery Status
[6 empty] | Screen Design | HTML Creation
Milestone - 1 | System Study & Analysis | Understand the client Business Requirement and Design the technical document
Perpair the list of task based upon client requirement & create the list of questions list implementation
Review the FSD Document
HTML Slicing Based on Bootstrap and Responsive HTML5
Cross Matching the HTML UI and take the confirmation from client on that
Database Schema Designing & define their Mapping Using DB Tool + Define the User Roles in System
Design the ER Diagram for System Database
Milestone - 2 | College Management | Manage College Add/edit/delete
College Search Implementation
| Patient Management | Dashboard Implementation
Registration In Patient Portal
My Profile Management
Patient Login / Logout / Forgot Password / Change Password Implementation
| Provider Management | Registration In Provider Portal
My Profile Management
Provider Login / Logout / Forgot Password / Change Password Implementation
Dashboard Implementation
| 3rd Party Provider Management | Registration In Provider Portal
My Profile Management
Provider Login / Logout / Forgot Password / Change Password Implementation
Dashboard Implementation
Milestone - 3 | Patient Appointment Management | Provider Search Implementation
display the list of Providers & Pagination Implementation
Manage the filter & Provider Availibility Slots in System for Patient Appointment Booking
Send booking details to Provider
Email System for send direct email to Provider
Ask a Question Implementation
Send document to Provider System for dignosis Integration (Document Management)
Patient Profile view Page Implementation
Payment Gateway Implementation for Appointment Fees
Download Attached document & Treatment Plans, Healthcare Plan Records)& Validation for manage their limits (Download Management)
| Provider Schedule Management | Calendar Management For Schedule
Manage the Provider Time Slot Schedule
Gmail Import Integration for Appointment
Outlook Import Integration for Appointment
Email Integration for Session details
Provider Profile View Implementation
Schedule the Session with Doctor for Appointment Booking
| Stripe Payment Gateway | Setup the Configuration & Lib. In System for Implement in System
| (Super Admin) CMS Management | CMS Management for Setup the Application Pages
Manage Filter
Add/eDit/Delete Implementation
| Mail Template Management | Edit Template Content for Email
Mail template Integration in System
Search Implementation For Email Template
Mail Lib. Setup for Send the email in Inbox & Spam filteration
| Manage Transactions | Manage Stripe Payment Transactions At the Provider Portal
Manage Stripe Payment Transactions At the Patient Portal
Milestone -4 | My Appointments | Calendar Management for View Patient Booking
Filter Management in Calendar
Manage the Appointment Status (Confirmed/Decline/Awaiting Confirmation)
| Communication Logs | Manage Communication logs in system | display the list of last logs that during the video call sent , we manage it via chat schedules
Search Implementation in Logs
Data Saving during the Video Session & Manage UI
| Sessions Management | Manage Video call Session Schedule Between Patient and Provider
Email Notification for Video Conference
Manage Video Call History
Manage the Call Duration for 45 Minutes Session
|  | Video Plugins Implementation | Video Plugins Provide by Client and We Review those Plugins Before Implementation
Manage Communication logs in system
Milestone -5
| Appointment Management | Cancel Appointment Implementation & Release the Block Space
Send Email to Provider/Patient Regarding Appointment Update
|  | Refund the Payment Balance to Patient Account | we need to review the refund process via stripe payment gateway integration
Stripe Payment Gateway Integration
| College (ADMIN) Management | Manage Provider accounts Lists
Integrate the Search Feature in Provider Management
Review the Provider Profile & Their account Status
Manage Profile Integration
Dashboard Implementation
| Manage Provider (Counsellors) Calendar | Manage Provider Calendar
Manage the Provider Calendar Availity Time Slot Schedule
Gmail Import Integration for Appointment
Outlook Import Integration for Appointment
Manage Email Integration for Appointment Remove/Update
Patient Appointment Update, As per the Provider calendar Update
Milestone - 6 | BetterMynd Super Admin Portal
Milestone - 7 | System Testing | Testing the system with Test Case Scenario
Test the System for the Input data
Testing application with Test Data
Running Integration Test Cases
| User Acceptance Testing & Deployment | Testing with Client supplied database with some Real-time Scenarios
Review the system and Production Moving Plan
Final Test and Verify