## Delivery Plan
Better Mynd
# | Module |  | Sub Tasks | Pradeep Remarks | BA Hours | Development Hours | Designer Hours |  | QA Hours | Delivery | Milestone Delivery Date | Milestone Delivery Status
[7 empty] | UI View Design | HTML Creation
Milestone - 1 | System Study & Analysis |  | Understand the client Business Requirement and Design the technical document |  |  |  | 36 | 47
Perpair the list of task based upon client requirement & create the list of questions list implementation
Review the FSD Document
HTML Slicing Based on Bootstrap and Responsive HTML5
Cross Matching the HTML UI and take the confirmation from client on that
Database Schema Designing & define their Mapping Using DB Tool + Define the User Roles in System
Design the ER Diagram for System Database
Milestone - 2 | College (ADMIN) Management | Manage College Members Lists | Manage College Add/edit/delete |  |  | 10 |  |  | 6
|  |  | College Search Implementation |  |  | 4 |  |  | 3
| Patient Portal | Patient Management | Dashboard Implementation |  |  | 8 |  |  | 4
|  |  | Registration In Patient Portal |  |  | 6 |  |  | 3
|  |  | My Profile Management |  |  | 6 |  |  | 3
|  |  | Patient Profile view Page Implementation |  |  | 4 |  |  | 2
|  |  | Patient Login / Logout / Forgot Password / Change Password Implementation |  |  | 6 |  |  | 3
| Provider Portal | Campus Provider Management | Registration In Provider Portal |  |  | 5 |  |  | 3
|  |  | My Profile Management |  |  | 5 |  |  | 2
|  |  | Provider Profile View Page Implementation |  |  | 4 |  |  | 2
|  |  | Provider Login / Logout / Forgot Password / Change Password Implementation |  |  | 3 |  |  | 2
|  |  | Dashboard Implementation |  |  | 6 |  |  | 3
|  | 3rd Party Provider Management | Registration In Provider Portal |  |  | 6 |  |  | 3
|  |  | My Profile Management |  |  | 4 |  |  | 2
|  |  | Provider Profile View Page Implementation |  |  | 3 |  |  | 2
|  |  | Provider Login / Logout / Forgot Password / Change Password Implementation |  |  | 2 |  |  | 1
|  |  | Dashboard Implementation |  |  | 6 |  |  | 3
Unit Testing Lists Creation , Meeting , Co-ordination with BA/QA related to the functional things & dependencies (Estimated Hours)
| QA | Review the flow and update on bugs to developers
BA review the application and demostrate to client accordingly
[6 empty] | 88 |  |  | 47
Milestone - 3 | Patient Portal | Appointment Schedule | Provider Search Implementation |  |  | 7 |  |  | 3
|  |  | display the list of Providers & Pagination Implementation |  |  | 6 |  |  | 3
|  |  | Manage the filter & Provider Availibility Slots in System for Patient Appointment Booking |  |  | 16 |  |  | 8
|  |  | Send booking details to Provider |  |  | 6 |  |  | 3
|  |  | Email System for send direct email to Provider |  |  | 6 |  |  | 3
|  |  | Ask a Question Implementation |  |  | 8 |  |  | 4
|  |  | Payment Gateway Implementation for Appointment Fees |  |  | 10 |  |  | 8
|  | Document Management | Send document to Provider System for dignosis Integration (Document Management) |  |  | 6 |  |  | 3
|  |  | Download Attached document & Treatment Plans, Healthcare Plan Records)& Validation for manage their limits (Download Management) |  |  | 8 |  |  | 5
| Provider Portal | Appointment Schedule | Calendar Management For Schedule |  |  | 16 |  |  | 8
|  |  | Manage the Provider Time Slot Schedule |  |  | 5 |  |  | 3
|  |  | Gmail Import Integration for Appointment |  |  | 6 |  |  | 3
|  |  | Outlook Import Integration for Appointment |  |  | 6 |  |  | 3
|  |  | Email Integration for Session details |  |  | 6 |  |  | 3
|  |  | Schedule the Session with Doctor for Appointment Booking |  |  | 8 |  |  | 4
|  | Stripe Payment Gateway | Setup the Configuration & Lib. In System for Implement in System |  |  | 15 |  |  | 8
Implement the Live Account details with Payment Gateways
|  | Manage Transactions | Manage Stripe Payment Transactions At the Provider Portal |  |  | 8 |  |  | 5
Manage Stripe Payment Transactions At the Patient Portal
| Super Admin Portal | CMS Management | CMS Management for Setup the Application Pages |  |  | 5 |  |  | 3
|  |  | Manage Filter |  |  | 3 |  |  | 2
|  |  | Edit CMS Pages Contents Implementation | We Provide the Pages in System Client can only update the content on those pages, Can't Create New Page Only System contents client can manage. |  | 6 |  |  | 3
|  | Mail Template Management | Edit Template Content for Email |  |  | 8 |  |  | 3
|  |  | Mail template Integration in System |  |  | 20 |  |  | 8
Search Implementation For Email Template
Mail Lib. Setup for Send the email in Inbox & Spam filteration
Unit Testing Lists Creation , Meeting , Co-ordination with BA/QA related to the functional things & dependencies (Estimated Hours)
| QA | Review the flow and update on bugs to developers
BA review the application and demostrate to client accordingly
[6 empty] | 185 |  |  | 96
Milestone -4 | Provider Portal | My Appointments | Calendar Management for View Patient Booking |  |  | 16 |  |  | 8
Filter Management in Calendar
Manage the Appointment Status (Confirmed/Decline/Awaiting Confirmation)
| Patient & Provider Portal | Communication Logs | Manage Communication logs in system | display the list of last logs that during the video call sent , we manage it via chat schedules |  | Estimation depends on Video Module, If they Provide then estimation managed accordingly.
Search Implementation in Logs
|  |  | Data Saving during the Video Session & Manage UI |  |  | 8 |  |  | 4
|  | Sessions Management | Manage Video call Session Schedule Between Patient and Provider |  |  | 20 |  |  | 12
Email Notification for Video Conference
Manage Video Call History
|  |  | Manage the Call Duration for 45 Minutes Session |  |  | 8 |  |  | 4
|  |  | Video Plugins Implementation | Video Plugins Provide by Client and We Review those Plugins Before Implementation |  | Under discussion client Suggest some Video Modules We are still doing some POC, Will commit Estimation Soon.
Unit Testing Lists Creation , Meeting , Co-ordination with BA/QA related to the functional things & dependencies (Estimated Hours)
| QA | Review the flow and update on bugs to developers
BA review the application and demostrate to client accordingly
[6 empty] | 56 |  |  | 28
Milestone -5
| College (ADMIN) Management | Appointment Management | Cancel Appointment Implementation & Release the Block Space |  |  | 4 |  |  | 2
|  |  | Send Email to Provider/Patient Regarding Appointment Update |  |  | 3 |  |  | 2
|  |  | Refund the Payment Balance to Patient Account | we need to review the refund process via stripe payment gateway integration. If not Stripe not works with Refund solution then we mangae the Wallet and Estimation will update. |  | we need to review the refund process via stripe payment gateway integration. If not Stripe not works with Refund solution then we mangae the Wallet and Estimation will update.
Stripe Payment Gateway Integration
|  | Provider Management | Manage Provider accounts Lists |  |  | 5 |  |  | 3
|  |  | Integrate the Search Feature in Provider Management |  |  | 3 |  |  | 1
|  |  | Review the Provider Profile & Their account Status |  |  | 3 |  |  | 1
|  |  | Manage Profile Integration |  |  | 8 |  |  | 4
Dashboard Implementation
|  | Manage Provider (Counsellors) Calendar | Manage Provider Calendar |  |  | 24 |  |  | 12
Manage the Provider Calendar Availity Time Slot Schedule
Gmail Import Integration for Appointment
Outlook Import Integration for Appointment
Manage Email Integration for Appointment Remove/Update
Patient Appointment Update, As per the Provider calendar Update
Unit Testing Lists Creation , Meeting , Co-ordination with BA/QA related to the functional things & dependencies (Estimated Hours)
| QA | Review the flow and update on bugs to developers
BA review the application and demostrate to client accordingly
[6 empty] | 50 |  |  | 25
Milestone - 6 | BetterMynd Super Admin Portal |  | Login/Logout/Change password |  |  | 3 |  |  | 1
Change Password for Super Admin Profile
|  |  | Manage Super User Profile information |  |  | 3 |  |  | 1
|  |  | Manage Site Basic Settings |  |  | 2 |  |  | 1
|  | College Portal | Setup the Sub Portal for College |  |  | 10 |  |  | 6
|  |  | Manage College Accounts Status |  |  | 3 |  |  | 1
|  |  | Add/Edit/Delete College Admin Account |  |  | 10 |  |  | 4
|  | Production Deployment | Setp the Script on client Server , Configuration Settings |  |  | 15 |  |  | NA
Review the Client Server Dependencies and Installation
Unit Testing Lists Creation , Meeting , Co-ordination with BA/QA related to the functional things & dependencies (Estimated Hours)
| QA | Review the flow and update on bugs to developers
BA review the application and demostrate to client accordingly
[6 empty] | 46 |  |  | 14
Milestone - 7 | System Testing |  | Testing the system with Test Case Scenario
Test the System for the Input data
Testing application with Test Data
Running Integration Test Cases
| User Acceptance Testing & Deployment |  | Testing with Client supplied database with some Real-time Scenarios
Review the system and Production Moving Plan
Final Test and Verify