## Delivery Plan
Better Mynd
# | Module |  | Sub Tasks | Pradeep Remarks | BA Hours | Development Hours | Designer Hours |  | QA Hours | Development Delivery | Resource Name | QA Delivery | Milestone Delivery Date | Milestone Delivery Status
[7 empty] | UI View Design | HTML Creation
Milestone - 1 | System Study & Analysis |  | Understand the client Business Requirement and Design the technical document |  |  |  | 36 | 47
Perpair the list of task based upon client requirement & create the list of questions list implementation
Review the FSD Document
HTML Slicing Based on Bootstrap and Responsive HTML5
Cross Matching the HTML UI and take the confirmation from client on that
Database Schema Designing & define their Mapping Using DB Tool + Define the User Roles in System
Design the ER Diagram for System Database
Milestone - 2 | College (ADMIN) Management | Manage College Members Lists | Manage College Add/edit/delete |  |  | 10 |  |  | 6 | 2016-02-12 | Rohit
|  |  | College Search Implementation |  |  | 4 |  |  | 3
| Patient Portal | Patient Management | Dashboard Implementation |  |  | 8 |  |  | 4 | -
|  |  | Registration In Patient Portal |  |  | 6 |  |  | 3 | 2016-03-12 | Kamlesh
|  |  | My Profile Management |  |  | 6 |  |  | 3 | 2016-06-12 | Kamlesh
|  |  | Patient Profile view Page Implementation |  |  | 4 |  |  | 2 |  | Kamlesh
|  |  | Patient Login / Logout / Forgot Password / Change Password Implementation |  |  | 6 |  |  | 3 |  | Kamlesh
| Provider Portal | Campus Provider Management | Registration In Provider Portal |  |  | 5 |  |  | 3 | 2016-03-12 | Rohit
|  |  | My Profile Management |  |  | 5 |  |  | 2 | 2016-06-12 | Rohit
|  |  | Provider Profile View Page Implementation |  |  | 4 |  |  | 2 |  | Rohit
|  |  | Provider Login / Logout / Forgot Password / Change Password Implementation |  |  | 3 |  |  | 2 |  | Rohit
|  |  | Dashboard Implementation |  |  | 6 |  |  | 3 | -
|  | 3rd Party Provider Management | Registration In Provider Portal |  |  | 6 |  |  | 3 | 2016-08-12 | Rohit
|  |  | My Profile Management |  |  | 4 |  |  | 2 | 2016-09-12 | Rohit
|  |  | Provider Profile View Page Implementation |  |  | 3 |  |  | 2 |  | Rohit
|  |  | Provider Login / Logout / Forgot Password / Change Password Implementation |  |  | 2 |  |  | 1 |  | Rohit
|  |  | Dashboard Implementation |  |  | 6 |  |  | 3 | -
Unit Testing Lists Creation , Meeting , Co-ordination with BA/QA related to the functional things & dependencies (Estimated Hours)
| QA | Review the flow and update on bugs to developers
BA review the application and demostrate to client accordingly
[6 empty] | 88 |  |  | 47 | 2016-10-12 | Rohit Finish Bugs QA
Milestone - 3 | Patient Portal | Appointment Schedule | Provider Search Implementation |  |  | 7 |  |  | 3 | 2016-07-12 | Kamlesh
|  |  | display the list of Providers & Pagination Implementation |  |  | 6 |  |  | 3 |  | Kamlesh
|  |  | Manage the filter & Provider Availibility Slots in System for Patient Appointment Booking |  |  | 16 |  |  | 8 | 13/12/2016 | Rohit
|  |  | Send booking details to Provider |  |  | 6 |  |  | 3 | 14/12/2016 | Rohit
|  |  | Email System for send direct email to Provider |  |  | 6 |  |  | 3 | 14/12/2016 | Rohit
|  |  | Ask a Question Implementation |  |  | 8 |  |  | 4 | 2016-10-12 | Harsha
|  |  | Payment Gateway Implementation for Appointment Fees |  |  | 10 |  |  | 8 | 2016-12-12 | Rohit
|  | Document Management | Send document to Provider System for dignosis Integration (Document Management) |  |  | 6 |  |  | 3 | 2016-09-12 | Kamlesh
|  |  | Download Attached document & Treatment Plans, Healthcare Plan Records)& Validation for manage their limits (Download Management) |  |  | 8 |  |  | 5 |  | Kamlesh
| Provider Portal | Appointment Schedule | Calendar Management For Schedule |  |  | 16 |  |  | 8 | 2016-12-19 | Rohit
|  |  | Manage the Provider Time Slot Schedule |  |  | 5 |  |  | 3 |  | Rohit
|  |  | Gmail Import Integration for Appointment |  |  | 6 |  |  | 3 |  | Rohit
|  |  | Outlook Import Integration for Appointment |  |  | 6 |  |  | 3 |  | Rohit
|  |  | Email Integration for Session details |  |  | 6 |  |  | 3 |  | Rohit
|  |  | Schedule the Session with Doctor for Appointment Booking |  |  | 8 |  |  | 4 |  | Rohit
|  | Stripe Payment Gateway | Setup the Configuration & Lib. In System for Implement in System |  |  | 15 |  |  | 8 | 2016-12-19 | Pradeep/Rohit
|  |  | Implement the Live Account details with Payment Gateways | [7 empty] | Pradeep/Rohit
|  | Manage Transactions | Manage Stripe Payment Transactions At the Provider Portal |  |  | 8 |  |  | 5 | 2016-12-19 | Harsha
|  |  | Manage Stripe Payment Transactions At the Patient Portal | [7 empty] | Harsha
| Super Admin Portal | CMS Management | CMS Management for Setup the Application Pages |  |  | 5 |  |  | 3 | 2016-07-12 | Harsha
|  |  | Manage Filter |  |  | 3 |  |  | 2 |  | Harsha
|  |  | Edit CMS Pages Contents Implementation | We Provide the Pages in System Client can only update the content on those pages, Can't Create New Page Only System contents client can manage. |  | 6 |  |  | 3 |  | Harsha
|  | Mail Template Management | Edit Template Content for Email |  |  | 8 |  |  | 3 | 2016-09-12 | Harsha
|  |  | Mail template Integration in System |  |  | 20 |  |  | 8 |  | Harsha
|  |  | Search Implementation For Email Template | [7 empty] | Harsha
|  |  | Mail Lib. Setup for Send the email in Inbox & Spam filteration | [7 empty] | Harsha
Unit Testing Lists Creation , Meeting , Co-ordination with BA/QA related to the functional things & dependencies (Estimated Hours)
| QA | Review the flow and update on bugs to developers
BA review the application and demostrate to client accordingly
[6 empty] | 185 |  |  | 96 | 19/12/2016
Milestone -4 | Provider Portal | My Appointments | Calendar Management for View Patient Booking |  |  | 16 |  |  | 8 | 20/12/2016 | Kamlesh / Harsha
|  |  | Filter Management in Calendar | [7 empty] | Harsha
|  |  | Manage the Appointment Status (Confirmed/Decline/Awaiting Confirmation) | [7 empty] | Kamlesh
| Patient & Provider Portal | Communication Logs | Manage Communication logs in system | display the list of last logs that during the video call sent , we manage it via chat schedules |  | Estimation depends on Video Module, If they Provide then estimation managed accordingly. |  |  |  | 19/12/2016 | Harsha / Kamlesh
|  |  | Search Implementation in Logs | [6 empty] | 20/12/2016 | Harsha
|  |  | Data Saving during the Video Session & Manage UI |  |  | 8 |  |  | 4 | 20/12/2016 | Harsha
|  | Sessions Management | Manage Video call Session Schedule Between Patient and Provider |  |  | 20 |  |  | 12 | 2016-12-17 | Kamlesh
Email Notification for Video Conference
Manage Video Call History
|  |  | Manage the Call Duration for 45 Minutes Session |  |  | 8 |  |  | 4
|  |  | Video Plugins Implementation | Video Plugins Provide by Client and We Review those Plugins Before Implementation |  | Under discussion client Suggest some Video Modules We are still doing some POC, Will commit Estimation Soon.
Unit Testing Lists Creation , Meeting , Co-ordination with BA/QA related to the functional things & dependencies (Estimated Hours)
| QA | Review the flow and update on bugs to developers
BA review the application and demostrate to client accordingly
[6 empty] | 56 |  |  | 28 | 21/12/2016
Milestone -5
| College (ADMIN) Management | Appointment Management | Cancel Appointment Implementation & Release the Block Space |  |  | 4 |  |  | 2 | 22/12/2016 | Kamlesh/Pradeep
|  |  | Send Email to Provider/Patient Regarding Appointment Update |  |  | 3 |  |  | 2
|  |  | Refund the Payment Balance to Patient Account | we need to review the refund process via stripe payment gateway integration. If not Stripe not works with Refund solution then we mangae the Wallet and Estimation will update. |  | we need to review the refund process via stripe payment gateway integration. If not Stripe not works with Refund solution then we mangae the Wallet and Estimation will update.
Stripe Payment Gateway Integration
|  | Provider Management | Manage Provider accounts Lists |  |  | 5 |  |  | 3 | 5/1/2016 to 07/1/2016 | Harsha
|  |  | Integrate the Search Feature in Provider Management |  |  | 3 |  |  | 1
|  |  | Review the Provider Profile & Their account Status |  |  | 3 |  |  | 1
|  |  | Manage Profile Integration |  |  | 8 |  |  | 4 | 2017-09-01 | Harsha
Dashboard Implementation
|  | Manage Provider (Counsellors) Calendar | Manage Provider Calendar |  |  | 24 |  |  | 12 | 22/12/2016 | Rohit
Manage the Provider Calendar Availity Time Slot Schedule
Gmail Import Integration for Appointment
Outlook Import Integration for Appointment
Manage Email Integration for Appointment Remove/Update
Patient Appointment Update, As per the Provider calendar Update
Unit Testing Lists Creation , Meeting , Co-ordination with BA/QA related to the functional things & dependencies (Estimated Hours)
| QA | Review the flow and update on bugs to developers
BA review the application and demostrate to client accordingly
[6 empty] | 50 |  |  | 25 | 2016-12-23
Milestone - 6 | BetterMynd Super Admin Portal |  | Login/Logout/Change password |  |  | 3 |  |  | 1 |  | Kamlesh
|  |  | Change Password for Super Admin Profile | [7 empty] | Kamlesh
|  |  | Manage Super User Profile information |  |  | 3 |  |  | 1 |  | Kamlesh
|  |  | Manage Site Basic Settings |  |  | 2 |  |  | 1 |  | Kamlesh
|  | College Portal | Setup the Sub Portal for College |  |  | 10 |  |  | 6 |  | Pradeep / Rohit
|  |  | Manage College Accounts Status |  |  | 3 |  |  | 1 |  | Kamlesh
|  |  | Add/Edit/Delete College Admin Account |  |  | 10 |  |  | 4 |  | Kamlesh
|  | Production Deployment | Setp the Script on client Server , Configuration Settings |  |  | 15 |  |  | NA |  | Pradeep / Rohit
Review the Client Server Dependencies and Installation
Unit Testing Lists Creation , Meeting , Co-ordination with BA/QA related to the functional things & dependencies (Estimated Hours)
| QA | Review the flow and update on bugs to developers
BA review the application and demostrate to client accordingly
[6 empty] | 46 |  |  | 14 | 30/12/2016
Milestone - 7 | System Testing |  | Testing the system with Test Case Scenario
Test the System for the Input data
Testing application with Test Data
Running Integration Test Cases
| User Acceptance Testing & Deployment |  | Testing with Client supplied database with some Real-time Scenarios
Review the system and Production Moving Plan
Final Test and Verify
425

## Harsha
Milestone | Module | Estimated time | Actual Time | Resource | Delivery Date | Comments | Date
Milestone 2 | Patient Management | 6 | 2.5 | Harsha Khandelwal |  | Registration In Patient Portal | 2016-01-12
Milestone 2 | 3rd Party Provider Management | 6 | 2 | Harsha Khandelwal |  | Registration In 3rd Party Provider Portal | 2016-01-12
Milestone 2 | Patient Management | 6 | 4.5 | Harsha Khandelwal |  | My Profile Management | 2016-02-12
Milestone 2 | Campus Provider Management | 5 | 3 | Harsha Khandelwal |  | My Profile Management | 2016-02-12
Milestone 2 | Third Party Profile |  | 2 | Sourabh Tejawat |  | My Profile Management | 2016-03-12
Milestone 2 | Third Party Profile |  | 1.5 | Sourabh Tejawat |  | Upload multiple counseling certifications | 2016-03-12
Milestone 2 | Third Party Profile | 4 | 1.5 | Harsha Khandelwal |  | Update third party profile after login with third party | 2016-05-12
Milestone 2 | Third Party Profile | 4 | 2.5 | Harsha Khandelwal |  | Display multiple certifications and upload certifications with validations | 2016-05-12
Milestone 2 | Patient Management | 6 | 1.5 | Harsha Khandelwal |  | Updates on patient profile | 2016-05-12
Like : College ID Number Special Char. only - & _ allowed
is_profile_completeness field needs to be implement
In Profile By Default date not filled that I filled during the Registration --done
Update Profile Page BreadCrumb
Remove Notification & Message Icon from header

## Rohit
Milestone | Module | Estimated time | Actual Time | Resource | Delivery Date | Comments | Date

## Kamlesh
Milestone | Module | Estimated time | Actual Time | Resource | Delivery Date | Comments | Date
Milestone 4 | Patient & Provider Portal - Sessions Management | 28 | 1.25 | kamlesh sindhal | 2016-12-17 | R&D for video calling and chat module | 2016-11-30
Milestone 3 | Provider Portal - Stripe Payment Gateway | 15 | 1 | kamlesh sindhal | 2016-12-19 | R&D for stripe payment | 2016-11-30
Milestone 3 | Provider Portal - Appointment Schedule | 12 | 2 | kamlesh sindhal | 2016-12-19 | R&D for google calendar and outlook | 2016-11-30
Milestone 2 | Patient Portal - Patient Management - Registration In Patient Portal | 6 | 3 | kamlesh sindhal | 2016-03-12 | work on Patient Signup form - design , client side validation and server side | 2016-11-30
Milestone 2 | Patient Portal - Patient Management - Registration In Patient Porta | 6 | 1 | kamlesh sindhal | 2016-03-12 | work on Patient Signup form | 2016-12-01
Milestone 6 | BetterMynd Super Admin Portal - College Portal | 23 | 4.75 | kamlesh sindhal | 2016-12-23 | Work on add college and listing | 2016-12-01
Milestone 5 | College (ADMIN) Management - Provider Management | 11 | 1.75 | kamlesh sindhal | 2016-01-05 | Work on provider listing and change status | 2016-12-02
Milestone 6 | BetterMynd Super Admin Portal - College Portal | 23 | 2.5 | kamlesh sindhal | 2016-12-23 | Work on change status of college and edit college | 2016-12-02
Milestone 6 | BetterMynd Super Admin Portal - College Portal | 23 | 0.5 | kamlesh sindhal | 2016-12-23 | Work on activation mail sent to college user and change password | 2016-12-02
Milestone 5 | College (ADMIN) Management - Provider Management | 11 | 2.5 | kamlesh sindhal | 2016-01-05 | Work on edit provider | 2016-12-02
Milestone 5 | College (ADMIN) Management - Provider Management | 11 | 0.5 | kamlesh sindhal | 2016-01-05 | Mail send on status active or inactive in provider listing | 2016-12-03
Milestone 6 | BetterMynd Super Admin Portal - College Portal | 23 | 0.5 | kamlesh sindhal | 2016-12-23 | Mail send on status active or inactive in college listing | 2016-12-03
| Idle Timeout |  | 0.5 | kamlesh sindhal |  | Work on hippa compliance Idle Timeout fuctionallity | 2016-12-03
Milestone 3 | Provider Portal - Stripe Payment Gateway | 15 | 4 | kamlesh sindhal | 2016-12-19 | Work on Stripe Payment Gateway | 2016-12-03
| Work on college Registration |  | 1.5 | kamlesh sindhal |  | Work on college Registration | 2016-12-05
Milestone 3 | Patient Portal - Appointment Schedule - Payment Gateway Implementation for Appointment Fees | 10 | 3 | kamlesh sindhal | 2016-12-12 | Stripe Payment gateway callback and save detail in table | 2016-12-05
Milestone 3 | Provider Portal - Manage Transactions - Manage Stripe Payment Transactions At the Patient Portal | 8 | 2.5 | kamlesh sindhal | 2016-12-19 | Show transaction list in patient profile | 2016-12-05